## Basic Manual Gantt Chart
Task Name | Start Date | End Date | Duration | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5
Task Two | 2016-07-27 | 2016-08-01 | 5
Task Three | 2016-07-27 | 2016-08-04 | 8
Task Four | 2016-07-27 | 2016-08-06 | 10
Task Five | 2016-08-01 | 2016-08-09 | 8
Task Six | 2016-08-01 | 2016-08-05 | 4
Task Seven | 2016-08-03 | 2016-08-10 | 7
Task Eight | 2016-08-05 | 2016-08-12 | 7
Task Nine | 2016-08-06 | 2016-08-09 | 3
Task Ten | 2016-08-06 | 2016-08-10 | 4
Task Eleven | 2016-08-07 | 2016-08-13 | 6
Task Twelve | 2016-08-10 | 2016-08-16 | 6
Task Thirteen | 2016-08-14 | 2016-08-19 | 5
Task Fourteen | 2016-08-15 | 2016-08-23 | 8
Task Fifteen | 2016-08-16 | 2016-08-26 | 10
Task Sixteen | 2016-08-17 | 2016-08-28 | 11
Task Seventeen | 2016-08-18 | 2016-08-29 | 11
|  |  |  | Key: | Calculated Cell |  | Manual Entry Cell
[5 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual End Date
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5 | 2.5 | 2.5 | 50%
Task Two | 2016-07-27 | 2016-08-01 | 5 | 3.75 | 1.25 | 75%
Task Three | 2016-07-27 | 2016-08-04 | 8 | 2 | 6 | 25%
Task Four | 2016-07-29 | 2016-08-06 | 8 | 8 | 0 | 100%
Task Five | 2016-08-01 | 2016-08-09 | 8 | 6 | 2 | 75%
Task Six | 2016-08-01 | 2016-08-05 | 4 | 1.4 | 2.6 | 35%
Task Seven | 2016-08-03 | 2016-08-10 | 7 | 1.75 | 5.25 | 25%
Task Eight | 2016-08-05 | 2016-08-12 | 7 | 4.9 | 2.1 | 70%
Task Nine | 2016-08-03 | 2016-08-09 | 6 | 0.9 | 5.1 | 15%
Task Ten | 2016-08-06 | 2016-08-10 | 4 | 2.4 | 1.6 | 60%
Task Eleven | 2016-08-07 | 2016-08-13 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2016-08-10 | 2016-08-16 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2016-08-14 | 2016-08-19 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2016-08-15 | 2016-08-23 | 8 | 4 | 4 | 50%
Task Fifteen | 2016-08-16 | 2016-08-26 | 10 | 4 | 6 | 40%
Task Sixteen | 2016-08-17 | 2016-08-28 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2016-08-18 | 2016-08-29 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Members | Start Date in Number Form | 43164
Initiating the project / Milestone one | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100%
Meet with Client | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100% | All
Establish a brief | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100% | All
Establish expectations - us / client | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100% | All
Requirements | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100% | All
Define deliverables | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100% | All
Plannig the Project / Milestone Two | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75%
UML Diagram | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jesse
Choose interactive communitcation / pull | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | All
Choose UX methodology / Agile | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | All
Timeline / workflow | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jesse
Program Evaluation Research Task (PERT) | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jesse
Work breakdown structure (WBS) | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jesse
Choose / define frameworks | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 5% | All
Competitor analysis | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jordan
Identify Key content from brief | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | All
Select code methodologys | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | All
UX research / Card sorting / personas | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jesse
Identify key code content / calls to action / interactivity | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | All
Information Gathering | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jordan
Define team best practises / style guides | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Duke
Executing the project / Milestone Three | 2018-03-08 | 2018-03-24 | 16 | 0 | 16 | 0%
Lo-fi wire frames | 2018-03-08 | 2018-03-09 | 1 | 0 | 1 | 0% | Duke
User testing / feed back | 2018-03-08 | 2018-03-09 | 1 | 0 | 1 | 0% | All
Hi-fi wireframes | 2018-03-08 | 2018-03-09 | 1 | 0 | 1 | 0% | Duke
User & group testing / feed back | 2018-03-09 | 2018-03-10 | 1 | 0 | 1 | 0% | All
Coding | 2018-03-09 | 2018-03-21 | 12 | 0 | 12 | 0% | Duke / Jesse / Jordan
User testing / feed back | 2018-03-10 | 2018-03-26 | 1 | 0 | 1 | 0% | All
Client presentation | 2018-03-21 | 2018-03-22 | 1 | 0 | 1 | 0% | All
Project Hand over | 2018-03-22 | 2018-03-23 | 1 | 0 | 1 | 0% | All
Evaluation | 2018-03-23 | 2018-03-24 | 1 | 0 | 1 | 0% | All
Closure | 2018-03-23 | 2018-03-24 | 1 | 0 | 1 | 0%