## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Members | Start Date in Number Form | 43164
Initiating the project / Milestone one | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100%
Meet with Client | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100% | All
Establish a brief | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100% | All
Establish expectations - us / client | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100% | All
Requirements | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100% | All
Define deliverables | 2018-03-05 | 2018-03-06 | 1 | 1 | 0 | 100% | All
Plannig the Project / Milestone Two | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75%
UML Diagram | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jesse
Choose interactive communitcation / pull | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | All
Choose UX methodology / Agile | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | All
Timeline / workflow | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jesse
Work breakdown structure (WBS) | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jesse
Choose / define frameworks | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 5% | All
Competitor analysis | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jordan
Identify Key content from brief | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | All
Select code methodologys | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | All
UX research / Card sorting / personas | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jesse
Identify key code content / calls to action / interactivity | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | All
Information Gathering | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Jordan
Define team best practises / style guides | 2018-03-06 | 2018-03-09 | 3 | 2 | 1 | 75% | Duke
Executing the project / Milestone Three | 2018-03-08 | 2018-03-24 | 16 | 0 | 16 | 0%
Lo-fi wire frames | 2018-03-08 | 2018-03-09 | 1 | 0 | 1 | 0% | Duke
User testing / feed back | 2018-03-08 | 2018-03-09 | 1 | 0 | 1 | 0% | All
Hi-fi wireframes | 2018-03-08 | 2018-03-09 | 1 | 0 | 1 | 0% | Duke
User & group testing / feed back | 2018-03-09 | 2018-03-10 | 1 | 0 | 1 | 0% | All
Coding | 2018-03-09 | 2018-03-21 | 12 | 0 | 12 | 0% | Duke / Jesse / Jordan
User testing / feed back | 2018-03-10 | 2018-03-26 | 1 | 0 | 1 | 0% | All
Client presentation | 2018-03-21 | 2018-03-22 | 1 | 0 | 1 | 0% | All
Project evaluation | 2018-03-22 | 2018-03-23 | 1 | 0 | 1 | 0% | All
Project hand over | 2018-03-23 | 2018-03-24 | 1 | 0 | 1 | 0% | All
Closure | 2018-03-23 | 2018-03-24 | 1 | 0 | 1 | 0%
Key:
Deliverables